# Notes from ECOSUPPORT management telephone meeting June 10, 2010, 13:00-15:00.

Present: Eduardo Zorita (WP1), Brian MacKenzie (WP3), Urmas Raudsepp (WP4), Markus Meier (WP5, coordinator), Helén Andersson (notes).

| No. | Item | Responsible |
| --- | --- | --- |
| 1 | Minutes from the previous meeting Consortium Agreement signed by all partners. EPSS reporting system. Two deliverables still in “working mode”. (since the meeting one of the deliverables mentioned above has proceeded to “Submitted” status. All deliverables marked “DB” must be on the same format AREA(S) COVERED: [], TIME SPAN COVERED: []; TEMPORAL RESOLUTION (ifapplicable): []; SPATIAL RESOLUTION (if applicable): []; PARAMETRES INCLUDED:[]; MODEL APPLIED, WITH SOME INFORMATION ON CALLIBRATION & VALIDATION (applicable only for model-generated datasets): []; FORCING APPLIED (applicable only for model-generated datasets): []. Send information on progress, publications etc. to be included on the project webpage to Helén. | Bo, WP leaders WP leaders, Helén |
| 2 | WP Status reports (work progress, upcoming deliveries, delays etc.) WP5 Preparations/announcements for ECOSUPPORT Annual Meeting. Preparations/announcements for Climate Modelling School (together with Amber) Preparations/announcements for workshop on Uncertainties of scenario simulations (together with IBAM). Arrangement/notes for management group meetings. Preparations for WP4 meeting (together with WP4). Everybody involved will do a short presentation of work progress etc. Urmas will send out meeting agenda in August. A status report (just a few lines) will be written by WP5 leader. WP4 WP4 has no immediate deliverables. Progress is in accordance with plan. Model has been validated. Hindcast runs have been performed with HYPE river data. A status report (just a few lines) will be written by WP4 leader and be sent out to WP4 partners just to check that progress is ok everywhere. WP3 Workshop will be held in September. It would be useful to have WP2 representatives from BNI and IOW at the meeting. A follow-up meeting might take place in conjunction with the meeting days at SMHI in October. Brian will organize the meeting and send emails around to inform relevant participants. A status report (just a few lines) will be written by WP3 leader and be sent out to WP3 partners just to check that progress is ok everywhere. WP2 (WP2 not at this meeting but reported by emails from Kari and Bo). A WP2 workshop was held in Stockholm on the 5th of May. Data of cod reproduction volumes has been delivered. Work ongoing to have all models run with common initial conditions. Improvements and reruns still to be done, but will hopefully be finished by the end of the summer, both for hindcast and projection. Paper on model validation delayed. A status report (just a few lines) will be written by WP2 leader and be sent out to WP2 partners just to check that progress is ok everywhere WP1 Reconstructions of atmospheric forcing delivered. Reconstructions of runoff: data set of Omstedt and Hansson might not be sufficient for our purposes. Alternative ways to transform data is being explored. Nutrient scenario simulations: transients will not be available, only future time slices due to problems with initial conditions. Short status report is delivered and will be uploaded to web. | Markus, Helén Markus, Helén Markus, Helén Markus, Helén Markus Urmas Markus Urmas Brian Brian Bo Bo |
| 3 | ECOSUPPORT Dissemination Results to be sent in for usage in conferences where we promote ECOSUPPORT. All think about possible publications. Several in plan in WP2 and WP3. | All All |
| 4 | Upcoming activities Climate Modelling School 13 Oct 2010. Still available places. Motivate relevant PhD-students to register. Workshop on Uncertainties of Scenario Simulations, 14 Oct 2010. The workshop is a BONUS+ cluster activity from ECOSUPPORT and IBAM. Baltic Sea Science Conference 2011 St Petersburg BONUS+ final conference for scientists and stakeholders, 2011 Gothenburg. ICES 2011, Gdansk. Possible BONUS/ECPSUPPORT initiative for a session on climate impact on fisheries/foodweb. Draft proposal to be written by Brian with possible help of others (e.g. Thorsten B). | All Brian |
| 5 | BONUS Steering group/BONUS 169 Next call in Nov 2011 It is very important to do the BONUS on-line poll as this will be used to formulate the next call. A chance for us to stress the importance of continued research on physical aspects and the impact of climate change. Midterm assessment analysed. Not all PIs aware of their relevant stakeholders. Markus attended very interesting presentation on how burden of BAP implementation can be distributed, according to economist Markku Ollikainen, University of Helsinki (e.g. largest gain, pay countries where it is cheap to clean etc.). |  |
| 6 | Next meeting in conjunction with the Annual Assembly | Markus, Helén |